Annex 1: Terms of Reference (TOR)

Curriculum Development and Market Analysis services

In the scope of RECONOMY programme, Help – Hilfe zur Selbsthilfe (in further text referred to as Help) started the implementation of the project “Inclusive jobs in ICT” in Armenia, Georgia, Moldova and Ukraine, with the objective to enable women and youth up to 30 years of age, including the most disadvantaged and excluded groups, to benefit from economic opportunities by increasing their income and taking up decent/green employment/self-employment. The Programme is funded by the Swedish International Development Cooperation Agency (Sida) and is implemented jointly by HELVETAS Swiss Intercooperation (Helvetas) together with Help – Hilfe zur Selbsthilfe.

Part of the project strategic process is private sector engagement that focuses on a joint endeavour by the RECONOMY Programme and the private sector for greater scale, sustainability, and effectiveness of development outcomes. The project is built on three main pillars: skills and intermediation service development, business services development, and advocacy.

Background and Rationale

Help has concluded a Partnership Agreement with Armenian Code Academy to create important synergies and contribute to the goal of RECONOMY and the business/activity of Armenian Code Academy, eventually leading to better economic opportunities (income and jobs) for the target group. The purpose of the Agreement is to contribute to the long-term competitiveness and growth of Armenian professionals and enterprises in the gaming sector. Armenian Code Academy will develop two new game development courses for industry newcomers. Moreover, Armenian Code Academy will organise a game development conference together with industry main players to showcase the international presence and diversity of projects that they represent, as well as inform target audience on game dev. eco-system transformation.

Purpose of “Consultancy on Curriculum Development and Market Analysis ”

The purpose of consultancy on curriculum development and market analysis for a Game Development Course is to create a dynamic, industry-relevant educational program that not only meets current market demands but also anticipates and prepares students for the future landscape of game development. The collaboration with industry experts, adherence to educational standards, and a focus on continuous improvement are integral to the success of this purpose.

Final Outcome: Detailed Curriculum

Intended users of the “Consultancy on Curriculum Development and Market Analysis”

Armenian Code Academy

All services are intended to support Armenian Code Academy’s operation in Armenia; therefore, all service products and outputs will officially remain in the ownership of Armenian Code Academy.

Geographical Scope

The “Consultancy on Curriculum Development and Market Analysis”  must be carried out in:

•Yerevan, Armenia

Approach and Methodology

The candidate is open to provide the suggested methodology and approach based on which the  application will be selected.

Stakeholders to involve in the Service

Before conducting  the service, possible consultants will have an introductory meeting with the Armenian Code Academy’s Team in order to understand  the specific details of the project, such as the duration of the course, programming language that will be used etc.

Deliverables and Schedule

Deadline for submission of offer is 23th of December

Deadline for signing a contract with the service provider is 25th of December.

Deadline for starting the assignment is 25th of December

Deadline for submitting the final report is 10th of January. The final report will be submitted in English language and will include description of the undertaken activities, conclusions, and next steps.

Qualification requirements for the consultant:

- University Degree in Education, Curriculum Development, Instructional Design, Business, Communication and/or relevant field

- Proven track record of at least 5 years in curriculum development, instructional design, or a related educational role.

- In-depth understanding of the Game Development industry, including current trends, emerging technologies, and the skill sets in demand.

- Familiarity with the global landscape of game development education.

- Demonstrated ability to design and develop comprehensive and engaging curricula for educational programs.

- Experience in integrating practical, hands-on learning experiences into curriculum design.

- Proven experience in conducting thorough market analyses, particularly within the context of educational programs.

- Ability to identify industry needs, competitor strengths and weaknesses, and opportunities for differentiation.

- Excellent written and verbal communication skills.

- Ability to articulate complex educational concepts in a clear and accessible manner.

Required documents

- An updated CV of team leader or company profile

- Portfolio of completed assignments

- Methodology

- Proposal Submission Form Annex 2 – duly completed and signed and stamped by the Candidate

- Duly signed and stamped Annex 3 - Help General Terms and Conditions for Service Contracts

- Duly signed and stamped Annex 4 - Help Code of Conduct for Contractors

- Duly signed and stamped Annex 5 - Help Declaration for Tenderers, Candidates and Suppliers

For further information, please contact stamatovic@help-ev.de or via Phone Number: +382 69897919