| Technical Supervision for the Installation of the 3 septic tanks at wastewater hotspots of Gavar consolidated community, Gegharkunik administrative region, Armenia. | Project number/ cost centre: 18.2062.0-010.00 |
| --- | --- |

1.	List of abbreviations	2

2.	Context	3

3.	Meanings and definitions	5

4.	General information of the chosen hotspots at the Gavar districts	5

5.	Scope of the works to be supervised	6

6.	The criteria for the Supervisor	7

6.3.	The objectives of the technical supervision of the septic tanks’ construction	7

7.	Tasks to be conducted by the Supervisor	7

8.	Type of submission	10

9.	Period of assignment:	13

10.	Concept	13

Technical-methodological concept	13

Project management of the designer	14

11.	Personnel concept	14

Team leader (National)	14

Expert 1 (National)	15

Expert 2 (National)	15

12.	Costing requirements	15

Assignment of personnel	15

Travel	16

Other costs	16

13.	Requirements on the format of the bid	16

14.	Annexes	17

# List of abbreviations

| AVB | General Terms and Conditions of Contract (AVB) for supplying services and work 2018 |
| --- | --- |
| BMZ | Federal Ministry for Economic Cooperation and Development |
| CE | Cost Estimations |
| CR | Construction Register |
| Defect | Drawback, imperfection or defect occurred in the process of the civil works |
| DTD | Detailed Technical Design |
| EU | European Union |
| GIZ | Deutsche Gesellschaft für Internationale Zusammenarbeit |
| Machinery | Machinery and equipment required for the construction |
| MoEnv | Ministry of Environment of the Republic of Armenia |
| MSR | Monthly Summary Report |
| PCR | Project Completion Report |
| PE | Population equivalents |
| PIR | Project Inception Report |
| Site | Site for the construction of the building for upgrading Gavar mechanical WWTP |
| ToRs | Terms of reference |
| Veolia | Veolia Djur CJSC |
| WWT | Wastewater treatment |
| WWTP | Wastewater treatment plant |

# Context

Lake Sevan is the largest freshwater lake in the Caucasus Region and one of the largest freshwater high-mountain lakes of Eurasia. The Lake is fed by 28 rivers and streams, and the Hrazdan River flows out of it. Lake Sevan and some of its surrounding areas are designated as Sevan National Park. Lake Sevan is located in Gegharkunik Province of Armenia. Gegharkunik Province is currently divided into 5 urban agglomerations, that comprise 5 urban and 52 rural communities. Lake Sevan occupies the central part of the province, lying at a height of 1900 meters above sea-level. The climate of Gegharkunik Province is cold and snowy in winter, while the summer is characterized with warm and humid climate. The annual precipitation level ranges between 500 and 600 mm at below 2000 meters, while it may reach up to 1000 mm in the mountainous areas.

Intensive and unsustainable use of water during the past decades, and uncontrolled discharge of the impurified wastewater into the lake as well have led to a significant deterioration of both water quantity and quality. The lake faces numerous environmental challenges and has also suffered significant biodiversity loss.

Currently, there are three wastewater treatment plants (WWTP) in operation in Gegharkunik Province around Lake Sevan basin in the cities of Gavar, Martuni and Vardenis. These three plants are under the operation of Veolia, the private water operator in Armenia, which is a part of Veolia French Group. All three plants are designed only for mechanical treatment. There are no other wastewater treatment facilities around Lake Sevan, especially in the rural settlements right by the lake and the private households have their own septic tank systems (mostly pits).

Recent research approves the number of diffusive impurified wastewater discharge directly into the lake’s basin area without any initial processing. Situation worsens in the districts, where households have appropriate sewage pipes without further connection to the main sewer and generated wastewater finally discharges into ground and is absorbed in there. Thus, according to data, only about 50% of Gavar town, excluding consolidated communities, has centralised sewage system. The rest wastewater is discharged into generally non-impermeable pit latrines or septic tanks, with further absorbing into soil, or into some adjacent drain systems with the subsequent discharge into the basin. In this regard, one of the great polluters of the basin is agriculture sector, livestock farms. All this wastewater is saturated with phosphorous and nitrogen, main nutrients for the lake’s blooming. In other words, there is no complete treatment of wastewater that flows into Lake Sevan.

Since the Gegharkunik region’s landscape is complex, settlements are situated quite far from each other and there is quite big impact of anthropogenic activity, such as agriculture or cattle breeding, diffusive contamination of the lake plays significant role, so it is important to pilot some local and affordable solution for various type of contamination that will lighten the anthropogenic burden on the lake.

In this regard, establishment and further maintenance of the local, decentralized, small-scale WWT solutions, reflecting local needs, and partially that are efficient for phosphorous and nitrogen processing in wastewater is crucial for the wastewater effective management in this region.

Therefore, the EU4Sevan Component of ECOserve Project Programme together with Gavar municipality and local community representatives, revealed several hotspots of the unprocessed wastewater discharge into soil and Gavaraget River, which is the tributary of the Lake Sevan. Installation of the local WWT solutions on the ground will enhance the ecological and health situation of the adjacent districts and will support in improving the environmental conditions of Gavaraget river. Besides that, based upon such best local practices, it will be possible to scale-up such solution on the spot by the municipality in future.

Gegharkunik Marzpetaran and local communities will directly benefit from project measures to improve the environmental status of the Lake Sevan ecosystem, pilot measures for improved wastewater treatment.

The EU4Sevan Project: Environmental Protection of Lake Sevan Project is co-funded by the EU and the BMZ and jointly implemented under a Multi-Partner Contribution Agreement by GIZ and the United Nations Development Programme (UNDP).

The Project is part of the EU Action “EU4Energy Efficiency and Environment” and the BMZ- funded programme “Management of natural resources and safeguarding of ecosystem services for sustainable rural development in the South Caucasus” (ECOserve) and has been officially launched in September 2020.

The Project’s overall objective is to enhance the environmental protection of Lake Sevan, which is the largest freshwater lake in the Caucasus Region. Lake Sevan is the most significant source of freshwater, irrigation water, aquaculture, as well as hydropower in Armenia. Its condition has direct bearing on the region’s environmental health and Armenia’s economic potential.

EU4Sevan project has five key outputs:

- Output 1: The water monitoring and management capacities for Lake Sevan watershed are (further) improved.

- Output 2: The capacities for implementing ecosystem-friendly and water-protecting land-use and cultivation practices are improved.

- Output 3: The capacities for implementing wastewater treatment, including nature- based solutions, are improved.

- Output 4: Awareness and information availability for the protection of Lake Sevan is enhanced among basin communities, the private sector and other stakeholders.

- Output 5: The Lake Sevan ecosystem governance is further improved.

Outputs 1-4 are implemented by GIZ, and output 5 is implemented by UNDP. Main beneﬁciaries of the project are people living in Gegharkunik region.

The Ministry of Environment, Ministry of Territorial Administration and Infrastructure and Ministry of Economy are the main partners of the EU4Sevan project. The Ministry of Environment has a wide scope of authority for natural resources protection. Among other tasks, the Ministry implements strategic management, protection and allocation of water resources. The Ministry of Economy     is a partner, which is responsible in Armenia for the agricultural sector (among others), and the Ministry of Territorial Administration and Infrastructure which is in charge of local governance and infrastructure. Under the supervision of this ministry operates the Water Committee, which is a public agency that develops and implements the policy of the Government of Armenia regarding the management and use of state-owned water management systems which is given to Veolia, a private operator under the Lease Contract. In accordance with the Lease Contract, Veolia has committed to ensuring the production and sale of drinking water, wastewater treatment systems, to improve the development and distribution of residential distribution networks as a unified operator for 15 years starting from 1 January 2017.

The main beneficiaries of the project will be the Armenian citizens, in particularly those living in the communities situated near Lake Sevan: The total population living within boundaries of  Lake Sevan basin is approximately 212,238 permanent residents (about 58,045 urban, and 154,193 rural).

The local communities will directly benefit from project measures to improve the environmental   status of the Lake Sevan ecosystem, pilot measures for improved wastewater treatment.

## Meanings and definitions

Within the activity of this task, the following meanings and definitions are as follows:

- Client - a person or a body, which carries out the selection within the project and sign the contract with the Constructor for the execution of the works. At this case – GIZ,

- Constructor – a company selected by the client for the performance of the construction works,

- Supervisor – competent technical supervising firm, that will be recognized as a winner of the tender within the ToR.

# General information of the chosen hotspots at the Gavar districts

During the field studies and close cooperation with the Gavar municipality several hotspots were identified in the Gavar consolidated community.

### Hotspot at the Barekamutyan street of the Gavar city

The Hotspot is located at Gavar city, Barekamutyan street 42, (coordinates: 40,344710N, 45,133180E) where an apartment block with approximately 45-50 inhabitants is situated. Wastewater generated from this building flows to a septic tank, located nearby. The septic tank does not satisfy the apartment block’s residents’ communal needs because of its small capacity and impossibility to discharge into the main sanitation network because of the area’s isolation. The designer shall study the hotspots and develop the DTD on building new septic tanks (or to renovate the existing ones) with the required volume, using some biological treatment approaches on the ground, or to design a DTD for a local WWTP with another technology (i.e. Fixed Bed Biological Reactor, FBR). On the left side of the existing septic tank some agricultural area is situated and according to the Gavar municipality representatives, treated wastewater can be directed to irrigate this area in the future. Based on this requirement, treated wastewater shall meet the FAO irrigation standards. The apartment block is located about 300 m from the river․ The area is adjacent to the main road and is accessible for heavy equipment and machinery approach.

### Hotspot at the area of No1 kindergarten, located at the Noratus settlement, Gavar municipality

The hotspot is located at Noratus settlement of the Gavar consolidated community (coordinates: 40,372760N, 45,174090E). Currently, there are approximately 90 children, and 19 workers comprised in the kindergarten. Wastewater generated from this building flows underground, located in the area of the kindergarten and dissolves in there. Sanitation pipeline is available on the spot. The designer is recommended offering treating generated wastewater by building a new septic tank with the required volume, using some biological treatment approaches on the ground, or using a local WWTP with another technology (i.e. Fixed Bed Biological Reactor, FBR). Treated wastewater will be directed to irrigate this area in the future. Based on this requirement, treated wastewater shall meet the FAO irrigation standards. The kindergarten area is situated in the close neighborhood of one the Lake Sevan tributaries. The area is adjacent to the main road and is accessible for heavy equipment and machinery approach.

### Hotspot at the area of No2 kindergarten, located at the Noratus settlement, Gavar municipality

The hotspot is located at Noratus settlement of the Gavar consolidated community (coordinates: 40,380090N, 45,177600E). Currently, there are approximately 75 children, and 20 workers comprised in the kindergarten. Wastewater generated from this building are separated in two ways: first, is connected with the local septic tank, located at the kindergarten’s area, and mainly only wastewater generated by kitchen’s activity, discharges in there, and second flow discharges in underground and dissolves in there. Sanitation pipeline is available on the spot. The designer is recommended offering treating generated wastewater by building a new septic tank with the required volume, using some biological treatment approaches on the ground, or using a local WWTP with another technology (i.e. Fixed Bed Biological Reactor, FBR). Treated wastewater will be directed to irrigate this area in the future. Based on this requirement, treated wastewater shall meet the FAO irrigation standards. The area is adjacent to the main road and is accessible for heavy equipment and machinery approach.

## Scope of the works to be supervised

The scope of works implemented by the Constructor is presented below:

- Construction, installation, liability, training and handing over of 3 septic tanks for 2 kindergartens, located in Noratus settlement (90 children and 19 workers in first, and 75 children and 20 workers for second kindergarten) and for one apartment block with approximately 45-50 inhabitants, located in Gavar town.

  - Calculated outputs for these hotspots are as follows:

    - Kindergarten No1: Qdaily av.=8.3 m3/day

    - Kindergarten No2: Qdaily av.=7.1 m3/day

    - Apartment block: Qdaily av.=9.5 m3/day

- Harmonization of the construction sites with the surrounding landscape upon completion of physical activity on the Site.

- Providing training for the employees who will operate and maintain these units.

- Providing the liability and handing over procedures with the relevant authorities in compliance with the national regulations.

- Putting the facility into operation.

In turn, the scope of the work (see sections 6.3 and 7) implemented by the Supervisor shall include 1st, 2nd, and 5th points of this paragraph, and takes participation in 4th point implementation (if needed).

## The criteria for the Supervisor

The offer that is submitted by a bidder shall at least comprise approaches as follows:

  - Work Experience

The bidder or the bidder’s employees shall include general experience in technical supervision of quality of civil works and/or engineering, particularly in water systems, water supply and sanitation, buildings construction, water supply/wastewater engineering in the last 5 years. Execution of similar contracts during the last 5 years, as part of which the Supervisor provided technical supervision of reconstruction or construction of public and residential, and hydrotechnical facilities that were successfully completed.

  - Work plan

The bidder must submit a work plan showing how it is planned to organize and execute the various stages of the supervision.

## The objectives of the technical supervision of the septic tanks’ construction

On behalf of the Client, the Supervisor shall supervise all aspects of civil works implementation to the full and final completion, approval and taking over of the Project to the Client. All executed works and procurement shall conform to the architectural and engineering designs and specifications. National legal acts on construction, GIZ regulations, building codes and standards shall be met, and rules and regulations governing environmental safeguards shall be observed during the implementation process. Technical quality of workmanship performed shall be equal to that of national level public buildings in the Republic of Armenia. Prior to the handing over of the completed project to the Client, the Supervisor shall assist in obtaining final approval by all relevant authorities of all aspects of the project. In addition, the Supervisor shall assist the Client in the preparation of a List of Defects and oversee the rectification of identified defects. Also, the Supervisor shall assist the Client in the preparation of final accounts and the closure of the Civil Works Contract.

# Tasks to be conducted by the Supervisor

  - General

    - Within five (5) days after signing the Technical Supervision Contract, the Supervisor must be mobilized on the construction Site and start assessing  work. For the duration of the contract, the Constructor will make office space available for the Supervisor (if necessary). Technical supervision works will start from the date of mobilization on Site. The expected duration of the project is 4 months (including the liability period). However, the contractual obligations of the Supervisor shall remain in force until all defects have been rectified, all works have been approved and final accounts have been prepared for the complete project.

    - The Supervisor shall ensure its representative’s constant presence on the construction site by everyday visits during working hours, who shall be responsible for ongoing technical supervision of all activities on the Site. As required, the Supervisor shall call on specialist members of the Supervisor’s team to check and advise on technical issues related to the individual team member’s professional expertise. The Supervisor shall record all activities on the Site, including decisions made on technical, legislative and safety issues.

    - At regular intervals, the Supervisor shall organize and chair Site Meetings with the participation of authorized representatives of the Client, the Supervisor and the (Main) Constructor and potential sub-constructors, as required. The Supervisor shall prepare an agenda for the proceedings at the Meetings. The Supervisor shall take minutes from the Site meetings and keep them on record. The Supervisor shall prepare and submit to the Client monthly and final reports, highlighting any issues identified during the past month and the solutions agreed for their resolve. Minutes from Site Meetings held since last monthly reporting shall be attached to the monthly report. Based on the Supervisor’s monthly report the Client shall make performance-based payments of the Constructor and the Supervisor.

    - Technical supervision shall ensure that the quality of the work performed, materials, structures and items procured, as well as technological requirements for the work, comply with the architectural and engineering design specifications and cost estimate, applicable rules and standards established by the Government, and samples of construction materials approved by the Client.

    - Technical supervision shall be carried out through continuous inspections, documented in writing, and supported by test results, technical documentation and certificates of the purchased goods, measurement of quantities, and photographs. In consultation with the Client, the Supervisor shall inspect and accept building materials and other purchased items. Technical supervision shall verify that all activities on the construction site are carried out within the framework of the legislation regulating the construction, environmental and occupational safety.

    - The Client is entitled to terminate the Supervisor Contract in the case of the Supervisor's specialist or representative absence from the construction site for more than 3 consecutive days during construction.

  - Key Provisions

Key provisions by the Supervisor shall include (but not be limited to) the following:

- participate in marking the axes of buildings and structures, check and measure geodetic marks during construction,

- regularly check the quality and technological sequence of all performed construction and installation works, their compliance with the design, construction norms and rules, technical terms of special works,

    - check the availability of certificates, technical passports and analysis results confirming the quality of materials, constructions, structures and engineering equipment used in construction. In case of non-compliance with the requirements of the design and product quality, prohibit their use indicating this in the relevant acts,

    - record in the general construction register kept by the Constructor all remarks and warnings, detected defects and notes on setting the appropriate deadlines for their elimination,

- participate in author supervision, state urban development control and quality inspections of other authorized bodies and follow up on timely elimination of the identified defects;

- in case of incomplete works and significant defects, prepare the list, set deadlines and immediately notify the Client,

- make sure that the progress of the daily work, the number of structures, items, materials, etc. delivered to the construction site are regularly recorded in the general construction register, and make appropriate notes about them,

- compile and ratify the acceptance acts of the covered works together with the Constructor, submit them to the Customer prior to the approval of the relevant performance act,

    - approve performance acts prepared and submitted for payment by the Constructor, checking in advance and measuring in detail all the volumes of work, which are included in the act submitted by the Constructor; the Supervisor shall be fully responsible for the accuracy and quality of the work provided in the performance act,

    - record and present to the Client the volumes of work to be performed in excess of or beyond the Contract volumes, giving a professional conclusion on the need for their implementation in the form of a memo,

    - monitor and check the Constructor's compliance with safety norms and rules and their daily entries in the technical safety register,

    - sign construction completion acts, in case of non-approval of the acts, submit the reasons in writing within three days,

    - immediately inform the Client in case of detection of defects threatening the stability and security of buildings and structures,

    - do not accept construction-installation works performed in breach of the approved designs, technical conditions, construction norms and rules or containing low-quality materials, structures or constructions.

7.3.	Special Requirements

Laboratory testing of materials shall be performed by the Constructor. The Supervisor shall, on the written instruction of the Client, carry out tests of certain finished structures and building materials used in the construction. To carry out this work, the Supervisor must have the appropriate technical means or a Contract with a licensed organization performing similar work. All tests must be performed in accordance with current standards of the Republic of Armenia. The Supervisor must submit a price quote for laboratory tests. The preliminary list of planned tests is presented below (see Table 1):

Table 1.

| N | Test Type | Unit of measurement | Initial quantity |
| --- | --- | --- | --- |
| 1 | Non-destructive testing of concrete of structural elements by Schmidt hammer sclerometer | element | 3 |
| 2 | Degradation test of strength and density of concrete and reinforced concrete elements | piece | 3 |
| 3 | Compacted soil density test | sample | 3 |

- Should tests or inspections in addition to those presented in the table be required during construction, the unit cost of such work shall be determined through additional negotiations with the Supervisor within market prices.

- The actual payment for the performed tests shall be made based on the type and number of tests ordered by the Client, after the submission of the final results of the tests by the Supervisor and shall be paid within the amount provided for the tests together with the regular monthly performance payment.

The Supervisor shall be responsible for the reliability of the test and inspection results. In case any of the following events are detected during the construction process – including environmental and safety aspects, the Client will be entitled to deduct as a penalty from the Supervisor fee 10 per cent of the financial implications of the incident:

- the Client's specialists or other authorities find defects or works done with deviations from the design, which were not duly noticed by the Supervisor and were included in the list of works submitted for payment,

- or the volumes to be paid for the submitted works do not correspond to the volumes actually performed by that date.

## Type of submission

  - General

    - The Supervisor must conduct the technical supervision of the construction, liability and handing over processes in full compliance with the legislative and normative national legislation, including, but not limited to the as follows:

- Government decree of 29 October 2015, No1317-N,

- full accordance with GIZ regulations and norms,

- Urban Development Minister Order No 44 of 28.04.1998,

- Urban Development Minister Order No 41-N of 16.06.2008.

    - Immediately upon deployment on the Site, within 10 (ten) working days, the Supervisor shall prepare and submit to the Client a Project Inception Report (hereinafter PIR). PIR must include evaluation of the complete design package, i.e. of architectural and engineering projects and specifications, as well as other aspects related to the project implementation, including site conditions and project completion dates. PIR must reflect any issues identified by the Supervisor that may cause a problem during project implementation and suggest proactive solutions. PIR must be submitted to the Client to receive the latter's comments and/or approval no later than 2 (two) weeks after the Supervisor is located on the construction site. PIR must be submitted in both Armenian and English languages, in electronic and paper version in 2 (two) copies.

  - Monthly Summary Report

    - The Supervisor shall submit a Monthly Summary Report (hereinafter MSR) to the Client, which shall reflect all construction works, its comparison with the schedule, and other activities carried out during the reporting month. Throughout the provision of services, the Supervisor shall submit MSRs to the Client for comments and/or approval. The MSR shall be submitted both in Armenian and English, in electronic and paper versions, in 2 (two) copies during the first 5 (five) working days of the following month.

    - The MSR shall include summary information on construction progress, costs, problems identified and their solutions, latent works and test reports, as well as evaluation of the Contractor's work. MSR shall also reflect any deviations recorded during supervision and the notes on their elimination, deviations from cost estimates (CE), if any, changes made in CEs, certificates of conformity of quality of presented products, table of laboratory tests performed and their results, as well as professional conclusion on the results of laboratory tests, photos, etc. The MSR report must be accompanied by a schedule of visits or permanent attendance by relevant specialists, with the rates and remuneration amounts. The report must also include construction register entries and minutes of the site meetings.

    - The report must include an assessment of the progress of the construction work and its compliance with the work schedules and contractual deadlines. All information and data reflected in the reports shall be verified by the Client.

  - Construction Register

The Constructor shall prepare and maintain Construction Register (hereinafter CR), where all the activities on the construction site are recorded on a daily basis. CR entries shall be monitored by the Supervisor.

  - Meetings at the Construction Site

    - Regular meetings shall be held at the construction site throughout the project. Meetings at the construction site should be conducted by the Supervisor, who is responsible for preparing the meeting agenda. Participants of the meetings shall be the authorized representatives of the Client, Supervisor, Designer, Constructor and Subcontractors (if any) who worked on the project during the previous week or will work next week. In addition, technical supervisors of ongoing works shall participate in the Site meetings.

    - Agenda of Site meetings

The agenda of each meeting at the construction site shall inter alia include:

- list of participants,

- approval of the minutes of the previous meeting,

- measures taken to address the issues identified and discussed during the previous meeting,

- issues recorded and discussed during the current meeting,

- work progress,

- any other business.

    - Procedure for conducting meetings at the construction site

The Supervisor shall compile the minutes of the meeting and present them to each meeting participant for comments and/or approval. Issues to be discussed during each meeting at the construction site shall inter alia include:

- approval of the minutes of the previous meeting (if any),

- ongoing work and progress vs the work plan,

- workforce at the construction site: quantity and composition,

- supplied building materials: certificates and their approval status,

- laboratory and the construction site tests: documented results and their approval status,

- inspections of the work performed by experts: documented results and their approval status,

- payments against executed works: necessary documents and their approval status,

- works to be carried out: the identified problems and the required solutions,

- environmental measures: the identified problems and the required solutions,

- occupational safety measures: the identified problems and the required solutions,

- any other business.

### Project Completion Report

    - Immediately after completion of the construction works stipulated in the Contract, the Supervisor shall assist the Client in accepting and taking over the works from the Constructor. The Supervisor shall then assist the Client in drafting the final acts (Final Accounts) and concluding the Contract. Project Completion Report (hereinafter PCR) must include the list of architectural/engineering projects, specifications and volumes, modified orders, changes and additions, as well as a summary of the entire project implementation process. A List of Deficiencies must be attached to the PCR, specifying remedy measures and deadlines. PCR must be signed by the Supervisor Group Leader, Site Technical Supervisor and all relevant technical experts involved in the implementation of the project.

    - The PCR must be submitted to the Client 10 (ten) working days after the completion of the construction works and after receiving the latter's comments and/or approval. PCR must be submitted in Armenian and English, in electronic and paper versions, in 2 (two) copies.

Certain milestones, as laid out in the table 2 below, are to be achieved by certain dates during the contract term, and at particular locations:

Table 2.

| Milestone | Deadline/place/person responsible |
| --- | --- |
| Project Inception Report | Within 10 days after the contract signing |
| Monthly Summary Report | Within the first 5 working days of the following month |
| Project Completion Report | 10 working days after the completion of the construction works |
| Project Liability Report | 5 working days after the completion of the liability procedure |

# Period of assignment:

From October 2024 to January 2025

# Concept

In the bid, the bidder is required to clearly show how the objectives and tasks defined in the ToR are to be achieved, if applicable under consideration of further specific method-related requirements (technical-methodological concept). In addition, the bidder must describe the project management system for service provision.

## Technical-methodological concept

Strategy: The bidder is required to consider the tasks to be performed with reference to the objectives of the services put out to tender. Following this, the bidder presents and justifies the strategy with which it intends to provide the services for which it is responsible.

The bidder is required to explain its approach for coordination with the GIZ project.

The Supervisor manages costs and expenditures, accounting processes and invoicing in line with the requirements of GIZ. The Supervisor reports regularly to GIZ in accordance with the AVB of the GIZ from 2022.

The bidder is required to draw up a personnel assignment plan with explanatory notes that lists all the experts proposed in the bid; the plan includes information on assignment dates (duration and expert days) and locations of the individual members of the team complete with the allocation of work steps as set out in the schedule.

The bidder is required to present and explain its approach to steering the measures with the project partners and its contribution to the results-based monitoring system.

The bidder is required to describe the key processes for the services for which it is responsible and create a schedule that describes how the services are to be provided. In particular, the bidder is required to describe the necessary work steps and, if applicable, take account of the milestones and contributions of other actors.

## Project management of the designer

- The Supervisor is responsible for selecting and steering the experts (national) assigned to perform the tasks.

- The Supervisor makes available equipment and supplies (consumables) and assumes the associated operating and administrative costs.

- The Supervisor manages costs and expenditures, accounting processes and invoicing in line with the as national, so requirements of GIZ.

- The Supervisor reports monthly to GIZ, presenting interim progress of the civil works, in accordance with the AVB of the GIZ from 2022.

In addition to the reports required by GIZ in accordance with AVB, the Constructor submits the following reports:

  - Project Inception Report,

  - Monthly Summary Report,

  - Project Completion Report.

The bidder is required to draw up a personnel assignment plan with explanatory notes that lists all the experts proposed in the bid; the plan includes information on assignment dates (duration and expert days) and locations of the individual members of the team complete with the allocation of work steps as set out in the schedule.

# Personnel concept

The bidder is required to provide personnel who are suited, professional to filling the positions.

The staff of the Supervisor must include the following necessary specialists, who must have the appropriate qualification, issued by the licensing body of the State Committee for Urban Development of the Republic of Armenia, in accordance with the established procedure.

Key Experts:

## Team leader (National)

Tasks of the Team Leader

- Architect/Constructor, Engineer in water supply and sanitation, Team Leader, Site Technical Supervisor

Qualifications of Team Leader

- Education/training (2.1.1): University qualification (Diploma/Master) in Construction, Architecture, civil engineering, particularly in water systems, water supply, buildings construction, Water supply/Wastewater engineering,

- Language (2.1.2): Armenian,

- General professional experience (2.1.3): 7 years of relevant experience in a relevant sphere, preferably in terms of technical supervision of the construction of water systems/ wastewater treatment facilities,

- Specific professional experience (2.1.4): 5 years of relevant experience in the sphere of the wastewater treatment plants designing and construction, water sewerage systems, water supply or relevant sphere,

- Leadership/management experience (2.1.5): minimum 3 years of technical supervision experience in architecture and/or construction,

- Other (2.1.8): Knowledge in AUTOCAD

## Expert 1 (National)

Tasks of expert 1

- Specialist in electricity, electrotechnics and weak currents

Qualifications of expert 1

- Education/training (2.2.1): University qualification (Diploma/Master) in Electricity, electronic equipment, electrotechnician, electromechanics, or relevant specialization

- Language (2.2.2): Armenian

- General professional experience (2.2.3): 5 years of relevant experience in electricity, electrotechnics, or relevant sphere

- Specific professional experience (2.2.4): 5 years of experience and knowledge in electricity, electro-technological systems, installation, or relevant sphere.

## Expert 2 (National)

Tasks of expert 2

- Ecologist, environmentalist

Qualifications of expert 2

- Education/training (2.3.1): Ecology, environment, chemistry, biology, geography, geology, or relevant specialization

- Language (2.3.2): Armenian

- General professional experience (2.3.3): 10 years of relevant experience in environmental/ecological sphere, experience in international projects is plus

- Specific professional experience (2.3.4): 5 years of experience and knowledge in drafting drafts and proceeding on EIA and expertise, knowledge in provision permits for water use/discharge, air pollution permits, land acquisition, etc.

- Other (2.3.8): Knowledge in local procedural and environmental legislation

Soft skills of team members

In addition to their specialist qualifications, the following qualifications are required of team members:

- Team skills

- Initiative

- Communication skills

- Socio-cultural competence

- Efficient, partner- and client-focused working methods

- Interdisciplinary thinking

The bidder must provide a clear overview of all proposed experts and their individual qualifications. The bidder can hire other short-term, non-key specialists with the preliminary consultation with the Client.

# Costing requirements

## Assignment of personnel

Team Leader:	 Assignment for 80 expert days

Expert 1:	 Assignment for 3 expert days

Expert 2:	 Assignment for 3 expert days

National experts pool (Team Leader, Expert 1, Expert 2) cumulative number of working days: 86 days.

Soft skills of team members

In addition to the specialist qualifications, the following qualifications are required of the Expert 1 and other potential team members:

- Team skills

- Initiative

- Communication skills

- Socio-cultural competence

- Efficient, partner- and client-focused working methods

- Interdisciplinary thinking

The bidder must provide a clear overview of all proposed experts and their individual qualifications. The bidder can hire other short-term, non-key specialists with the preliminary consultation with the Client.

## Travel

The bidder is required to calculate the travel by the specified experts and the experts it has proposed based on the places of performance stipulated in Chapter 2 and 3 and list the expenses separately by daily allowance, accommodation expenses, flight costs and other travel expenses.

## Other costs

The bidder is required to justify and calculate the additional costs required for implementation of the assignment. The additional costs must be not higher than 7% of the estimated total project cost.

# Requirements on the format of the bid

The structure of the bid must correspond to the structure of the ToRs. It must be legible (font size 11 or larger) and clearly formulated. The bid is drawn up in English.

The CVs of the personnel proposed in accordance with Chapter 7 of the ToRs must be submitted using the format specified in the terms and conditions for application. The CVs shall not exceed 15 pages. The CVs must clearly show the position and job the proposed person held in the reference project and for how long. The CVs must be submitted in English.

If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment.

Please calculate your price bid based exactly on the aforementioned costing requirements. In the contract the designer has no claim to fully exhaust the days/travel/workshops/ budgets. The number of days/travel/workshops and the budget amount shall be agreed in the contract as ‘up to’ amounts. The specifications for pricing are defined in the price schedule.

# Annexes

    - Detailed Technical Design,

    - Bill of quantities.