Section 1 – General Information

| Solicitation Number: | EFRA-PROC-RFP-FO 17 |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Solicitation Type: | Request for Proposals (RFP) |  |  |  |  |
| Procurement Description: | The USAID Economic Foundations for a Resilient Armenia Activity (Economic Foundations) is seeking a local or international consulting firm to support the implementation of the Public Administration Reform Strategy through conducting functional and institutional assessment of public administration bodies responsible for economic governance. |  |  |  |  |
| Anticipated Period of Performance: | October 1, 2024 – September 30, 2025 |  |  |  |  |
| Place of Performance: | Yerevan, Armenia |  |  |  |  |
| Contracting Party: | CNFA For: USAID Under: USAID Economic Foundations for a Resilient Armenia |  |  |  |  |
| Release Date: | August 19, 2024 |  |  |  |  |
| Point of Contact for Questions and Offers: | Name: Title: Address: Email: |  | Anna Trdatyan Office & Procurement Manager #5/1 Hrachya Kochar, Yerevan, Armenia, 0010 procurement@cnfa-armenia.org |  |  |
| Questions: | Question Deadline August 27, 2024. 6:00 PM, Yerevan (GMT+4) |  |  |  |  |
|  | Instructions: Questions must be submitted in writing; phone calls will not be accepted. Only CNFA’s written answers will be considered official and carry weight in the solicitation and subsequent evaluation. Verbal information received from CNFA or any other entity should not be considered an official response to any questions. |  |  |  |  |
| Offers: | Offer Deadline: September 10, 2024. 6:00 PM, Yerevan (GMT+4) |  |  |  |  |
|  | Via: | ☒ Email |  | ☐ Hard copy | ☐ Email or Hard copy |
|  | Instructions: Reference the Solicitation Number in any response to this solicitation. Offers received after the specified time and date will be considered late and considered only at CNFA’s discretion. Offerors must strictly follow the deadlines provided in this solicitation to be considered for award. |  |  |  |  |
| Offer Validity: | Offers must remain valid for not less than 60 calendar days after the offer deadline. |  |  |  |  |
| Award: | The award will be made to the offeror who is determined to be the best offeror per the evaluation criteria and methodology provided herein. CNFA will not issue an award to different offerors, entities, or third parties other than the selected offeror which submits an offer in response to this solicitation. CNFA anticipates awarding a Fixed-Price Contract to the selected offeror. |  |  |  |  |
| Terms and Conditions: | The resultant award is subject to CNFA’s Standard Terms and Conditions as stipulated in Section 6. |  |  |  |  |

Section 2 – Scope of Procurement

- Introduction: CNFA is an international agricultural development organization that specializes in the design and implementation of sustainable, enterprise-based agricultural initiatives. CNFA implements USAID Economic Foundations for a Resilient Armenia Activity in Armenia (Economic Foundations), a USAID-funded project with the objective to support building a resilient Armenian economy. Among other initiatives, Economic Foundations supports public administration reform strategy implementation and the efforts under the Deputy Prime Minister’s Office that has initially agreed to select the Ministry of Economy as a pilot in Project Year 1.

The Public Administration Reform (PAR) Strategy of Armenia, adopted in 2022, marks a significant milestone in the country's post-independence era, focusing on a comprehensive agenda for modernizing the government system. This reform effort acknowledges the challenges faced before and during the 2020 crisis and aims to address deep-rooted problems within the government machinery. The key problems that are supposed to be solved with the new strategy are related to policy-making practices, services delivered to the citizens, human capacities, and institutional arrangements. Aligned with the whole-of-government paradigm, the strategy envisions a future state characterized by human-centric, sustainable, responsible, dynamic, innovative, and optimal features.

- Scope of Work: This solicitation aims to engage a local or international firm to support the Economic Foundations and the Government of Armenia (GOAM) in implementing public administration reform strategy Pillar III: Institutional Modernization. The goal is to enhance the efficiency of the state management system by developing methodological tools and legal regulations, including a unified methodology for functional analysis and organizational categorization of state bodies responsible for economic governance. The firm will conduct the functional analysis, categorize state bodies including office of the Prime Minister, and lead a comprehensive review and reorganization of state system bodies including office of the Prime Minister to remove redundant functions, functions duplications and overlaps, define missing functions, optimize and automate procedures, including assessment and forecasting of service/maintenance costs of state administration system bodies (share in total state budget costs). The assessment will be based on international best practices, involving an inventory and mapping of the current system, functional reviews to analyze procedures, identify issues, and develop comprehensive procedures. These tasks aim to enhance the public administration system in line with international standards.

  - Tasks:

Task 1: Methodological Framework for Functional and Institutional Review

- Develop a comprehensive methodology for functional and institutional review of public administration bodies responsible for economic governance: Ministry of Economy, Ministry of Finance, Ministry of Territorial Administration and Infrastructure, Ministry of High-Tech Industry, State Revenue Committee, Statistics Committee, their subordinate bodies and office of the Prime Minister, including Deputy Prime Ministers' offices.

- Design and implement tools for functional analysis to enable self-assessment and modernization recommendations.

- Clearly define the functional scopes and structures of public administration bodies.

- Propose a methodological framework for restructuring the institutional architecture of the public administration system.

- Study international experiences and identify best practices for potential application.

Task 2: Functional and Institutional Mapping, Inventory, and Review

- Review the draft inventory and map of the current state of the public administration system from the following perspective - scope of functions, institutional arrangements, annual budget, channels and scope of accountability, autonomy, scope of decision-making powers, personnel information, etc.

- Reflect on connections and clarify roles, tasks, and goals of each body.

- Describe functions and classify bodies by types such as policy development, regulation, service provision, coordination, control, and maintenance.

- Review the unified typology for the classification of public administration bodies.

- Clarify organizational and legal forms for similar functions and develop or refine definitions.

- Define classification criteria and create a digital register of public administration system bodies for further programs and analyses.

Task 3: Functional and Institutional Analysis

- Conduct functional and institutional reviews using the developed methodology.

- Map administrative and decision-making procedures and business processes in state administration bodies and related organizations.

- Analyze internal procedures supporting functions and accountability chains (both de jure and de facto).

- Identify problems, gaps, duplications, overlaps, and missing points in the functional structure.

- Group functions based on their relevance to government priorities and conduct sample interviews for data elaboration.

- Determine necessary staffing levels (quantity as well) and skills through discussions with department heads or coordinating specialists.

- Identify functions suitable for competitive private sector delegation.

- Provide a comprehensive analysis that reveal the bottlenecks within the existing functional and institutional (structural) setup based on primary and secondary data collection, legislation reviews, workshops, and interviews with relevant political officials.

Task 4: Recommendations for Enhancing Structure and Functionality

- Explore and document best international practices on functional and institutional setup in comparable countries with a parliamentary political system (minimum 5 cases).

- Conduct consultations with political decision-makers and experts to outline suitable models of institutional and functional restructuring.

- Develop methodologies and procedures for streamlining and functional and structural changes of state administration system bodies, including internal changes to optimize overlapping functions, defining missing functions and reduce hierarchical administration.

- Clarify the existing legal framework for functional and institutional restructuring and initiate changes in existing legal acts.

- Develop at least three functional descriptions with clear division of authority, management, and accountability lines for the mentioned bodies.

- Present a package of recommendations for analyzing and decision-making regarding public system body functions, focusing on reduction, simplification, grouping, separation, improvement, creation of new functions, and outsourcing of general functions.

- Develop a comprehensive set of functional standards for public administration bodies based on functional analysis and the general typology of the bodies.

- Present a package of recommendations for the Optimization of Support Functions within the Government of Armenia, based on the best international practice and baseline assessment, propose optimization models for support functions, taking into consideration automation and outsourcing possibilities.

- Provide training for relevant personnel within state administration bodies for conducting functional and structural analyses.

2.2 Deliverables:

| Deliverable | Deliverable Description | Anticipated Delivery Date |
| --- | --- | --- |
| 1. | Inception report, including a detailed implementation plan, including objectives and scope and approach of assessment, timeline and resources, discussed and agreed with Economic Foundations and USAID. | October 15, 2024 |
| 2. | Comprehensive methodology for functional and institutional assessment review, including tools for self-assessment and modernization and a unified methodology for determining the organizational type | November 30, 2024 |
| 3. | Structural and functional reengineering recommendations, including the examples of the best international practice | April 30, 2025 |
| 4. | Complete inventory and mapping of current public administration system, including digital register creation | June 25, 2025 |
| 5. | Finalized unified typology for classifying public administration bodies | June 30, 2025 |
| 6. | Comprehensive report on functional and institutional analysis, including identified issues, and recommendations for improving the structure and functionality of public administration bodies. | August 30, 2025 |
| 7. | Training program and materials for personnel responsible for functional and structural analysis | September 30, 2025 |

3. Geographic Code Compliance: Items offered must comply with USAID Geographic Code 937 and 110. For a list of Source/Nationality countries approved within this USAID Geographic Code, refer to ADS Chapter 310, Source and Nationality Requirements for Procurement of Commodities and Services Financed by USAID. Contact CNFA with any questions regarding Geographic Code compliance.

Chapter 310, Source and Nationality Requirements for Procurement of Commodities and Services Financed by USAID. Contact CNFA with any questions regarding Geographic Code compliance.

Section 3 – Evaluation Methodology and Criteria

The award will be made to a responsible offeror whose offer follows the RFP instructions, meets the eligibility requirements, and is determined via a trade-off analysis to be the best value based on the application of the below evaluation criteria. Best value determination will consider both technical and financial proposals, i.e., the best approach and anticipated results combined with a reasonable cost. Proposed costs must reflect and match the degree of sophistication of the technical approach. The number of points below indicates the relative importance of each criterion:

| Criteria/Criteria Description | Assigned Weight |
| --- | --- |
| Technical Merits of the Proposal | 30 |
| - The proposal will be judged on the proposed design and methodology that most effectively and efficiently reaches the goal and objectives of this RFP. For the technical proposal, the Offeror is required to provide a detailed description of how the RFP requested activities will be implemented. |  |
| Management, Personnel, and Resources | 20 |
| - The Proposed staff have the requisite experience and expertise to perform the scope of work, within an appropriate level of effort. Offeror will be evaluated on offered experts’ relevant experience with similar activities. USAID Economic Foundations will evaluate the qualification, knowledge, and involvement of the personnel in similar activities. |  |
| Past Performance | 30 |
| - The proposal will be evaluated on the Offeror’s experience in delivering similar work as requested in the RFP. - The offeror has a demonstrated capacity to design and develop the similar functional assessment as described in the scope of work. - Offeror has a minimum of five years of providing the similar services. |  |
| Cost Proposal | 20 |
| - The proposed budget will be assessed on the degree to which the budget reflects the actual requirements of the technical proposal and the costs included in the budget accurately represent the work effort described in the technical proposal. |  |
| Total | 100 |

Section 4 – Offer Format Instructions

Offers in response to this solicitation must comply with the following instructions:

- Submissions will be accepted in the following language(s): English

- Include the following in the offer footer:

  - Offeror name

  - Solicitation Number

  - Page Numbers

- Offer in the format provided in Annex 1

Section 5 – Complete Offer

A complete offer must include the following documents:

- Completed Annex 1: Offer Template

- Completed Anex 2: Offer

- Copy of the Offeror’s business license.

- At least two References

Section 6 – CNFA Terms and Conditions

1. Ethical and Business Conduct: CNFA is committed to integrity in procurement, and only selects offerors based on objective business criteria such as price and technical merit. CNFA does not tolerate fraud, collusion among offerors, falsified proposals/bids, bribery, or kickbacks. Any organization or individual violating these standards will be disqualified from this solicitation, barred from future procurement opportunities, and may be reported to both CNFA’s Client – as applicable – and the appropriate Office of the Inspector General.

Employees and agents of CNFA are strictly prohibited from asking for or accepting any money, fee, commission, credit, gift, gratuity, object of value or compensation from current or potential vendors or suppliers in exchange for or as a reward for business. Employees and agents engaging in this conduct are subject to termination and will be reported to CNFA’s Client – as applicable – and the appropriate Office of the Inspector General. In addition, CNFA will further inform these agencies of any Offerors’ offers of money, fee, commission, credit, gift, gratuity, object of value, or compensation to obtain business.

Please contact the designated Point of Contact on the Solicitation Cover Page with any questions or concerns regarding the above information or to report any potential violations. Potential violations may also be reported directly to CNFA’s Fraud Hotline in writing via email at FraudHotline@cnfa.org or you may make an anonymous report by phone, text, or WhatsApp to the CNFA Global Fraud Hotline at 202-991-0943.

2. Terms and Conditions: This Solicitation is subject to CNFA’s standard terms and conditions. Any resultant award will be governed by these terms and conditions; a copy of the full terms and conditions is available upon request. Please note the following terms and conditions will apply:

- CNFA’s standard payment terms are 30 calendar days after receipt and acceptance of any commodities or deliverables. Payment will only be issued to the entity submitting the offer in response to this Solicitation and identified in the resulting award; payment will not be issued to a third party.

- No commodities or services may be supplied that are manufactured or assembled in, shipped from, transported through, or otherwise involving any of the following countries: Cuba, Iran, North Korea, Syria.

- Any international air or ocean transportation or shipping carried out under any award resulting from this Solicitation must take place on U.S.-flag carriers/vessels unless otherwise approved by CNFA.

- United States law prohibits transactions with, and the provision of resources and support to, individuals and organizations associated with terrorism. The selected offeror under any award resulting from this Solicitation must ensure compliance with these laws.

- United States law prohibits engaging in any activities related to Trafficking in Persons. The selected offeror under any award resulting from this Solicitation must ensure compliance with these laws.

- The title to any goods supplied under any award resulting from this Solicitation shall pass to CNFA following delivery and acceptance of the goods by CNFA. Risk of loss, injury, or destruction of the goods shall be borne by the offeror until title passes to CNFA.

- The offeror is prohibited from providing certain telecommunications equipment or services as a substantial or essential component of any system, or as a critical technology as part of any system, produced by the following covered companies, and their subsidiaries and affiliates, in the performance of any resulting award: Huawei Technologies Company; ZTE Corporation; Hytera Communications Corporation; Hangzhou Hikvision Digital Technology Company; Dahua Technology Company; and any other company as determined by the United States Government. The offeror certifies it will not provide covered telecommunications equipment or services to CNFA in performance of the resulting award. If covered telecommunications equipment or services are offered, the offeror must disclose it.

3. Disclaimers: This is a Solicitation only. Issuance of this Solicitation does not in any way obligate CNFA, its project(s), or its client(s) to make an award or pay for costs incurred by potential offerors in the preparation and submission of an offer. In addition:

- Offerors are responsible for ensuring their offers are received by CNFA in accordance with the instructions, terms, and conditions described in this Solicitation; failure to adhere to instructions may lead to disqualification

- CNFA may cancel the Solicitation and not award at any time

- CNFA may reject any or all responses received

- Issuance of the Solicitation does not constitute award commitment by CNFA

- CNFA reserves the right to disqualify any offer based on offeror failure to follow the Solicitation instructions

- CNFA will not compensate offerors for response to the Solicitation

- CNFA reserves the right to issue award based on initial evaluation of offers without further discussion

- CNFA may negotiate with offerors for their best and final offer and/or request clarifications from any offeror prior to award

- CNFA reserves the right to increase or decrease its order for quantities or units with the selected offeror

- CNFA may reissue the Solicitation or issue formal amendments revising the original Solicitation specifications and evaluation criteria before or after receipt of proposals

- CNFA may modify the specifications without issuing a formal notice to all offerors when the revisions are immaterial to the scope of the Solicitation

- CNFA may choose to award only part of the activities in the Solicitation, or issue multiple awards, if in the best interest of CNFA

- CNFA reserves the right to waive minor offer deficiencies that can be corrected prior to award determination to promote competition

- Offerors understand that CNFA’s Client(s) is not a party to this Solicitation and the offeror agrees that any protest hereunder must be presented – in writing with full explanations – to CNFA for consideration. CNFA’s Client(s) will not consider protests regarding procurements carried out by CNFA. CNFA, at its sole discretion, will make a final decision on any protest for this procurement.

Annex 1 – Offer Template

The following cover letter must be placed on letterhead – if applicable – and completed/signed/stamped by a representative authorized to sign on behalf of the offeror:

PART 1 – COVER LETTER

To:		Anna Trdatyan

Office and Procurement Manager

#5/1 Hrachya Kochar

Yerevan, Armenia

procurement@cnfa-armenia.org

Reference: 	Solicitation no. EFRA-PROC-RFP-FO-017

To Whom It May Concern:

We, the undersigned, hereby provide the attached offer to perform all work required to complete the activities and requirements as described in the above-referenced Solicitation. Please find our offer attached.

We hereby acknowledge and agree to all terms, conditions, special provisions, and instructions included in the above-referenced Solicitation. We further certify that the below-named organization—as well as the organization’s principal officers and all commodities and services offered in response to this Solicitation—are eligible to participate in this procurement under the terms of this solicitation and under the applicable regulations.

Furthermore, we hereby certify that, to the best of our knowledge and belief:

- We have no close, familial or financial relationship with any CNFA, its project staff members, or its Client (as applicable);

- We have no close, familial or financial relationship with any other offerors submitting proposals in response to the above-referenced Solicitation;

- We and our principal offerors are not debarred, suspended, or otherwise considered ineligible for receiving US Government funds. We understand that CNFA will not make any award to an entity that is debarred, suspended, or considered ineligible by the US Government;

- The prices in our offer have been arrived at independently, without any consultation, communication, or agreement with any other offeror or competitor for the purpose of restricting competition;

- All information in our proposal and all supporting documentation is authentic and accurate;

- We understand and agree to CNFA’s prohibitions against fraud, bribery, and kickbacks;

- We understand and agree to CNFA’s prohibitions against funding or associating with individuals or organizations engaged in terrorism or trafficking in persons activities.

We hereby certify that the enclosed representations, certifications, and other statements are accurate, current, and complete:

| For: | Offeror Name: | Offerors must provide entity name, if applicable, here |
| --- | --- | --- |
| Submitted By: | Name: | Offerors must print name of the authorized person who completed this offer here |
|  | Title: | Offerors must provide title of the authorized person who completed this offer here |
|  | Signature: | Offerors must provide signature of the authorized person who completed this offer here |
|  | Date: | Offerors must indicate the date this offer was completed here |
| Organization Information: | Phone: | Offerors must provide phone number for contact if selected for negotiation or award here |
|  | Email: | Offerors must provide email for contact if selected for negotiation or award here |
|  | Address: | Offerors must provide address for contact if selected for negotiation or award here |
|  | Website: | Offerors must provide organization website, if applicable, here |
|  | Country of Nationality: | Offerors must indicate their country of legal organization, ownership, citizenship, or lawful permanent residence here |
|  | Registration or Taxpayer ID Number: | Offerors must provide registration and/or taxpayer ID number here |

PART 2 – OFFER

Offerors are instructed to complete this form and place it on the Offeror’s letterhead. Once completed, this form serves as the binding proposal in response to this solicitation and is valid for the period identified on the cover page of this Solicitation. Failure to submit the information required herein may lead to disqualification of the offer.

- Technical Proposal

In 1,000 words or less, provide a methodology and implementation plan for the tasks outlined in Section 2. In addition, list the team members who will be engaged in the implementation of this assessment and strategy development and detail their experience and qualifications (attach CVs – not included in the word count). Please include who will manage the team, key strategic and creative staff, and other resources, internal or external, that may be used. Please specify those tasks assigned to each employee and/or proposed consultant.

Offerors must respond to the prompt here.

  - Past Performance

Offerors are required to provide evidence of past performance responding to the criteria outlined below:

- Minimum of 7 years’ experience of conducting similar assessments.

- Experience in performing rigorous analysis as described in the scope of work in the last 5 years and communicating with high-level government officials and stakeholders.

Offerors must complete five (5) past performance reference forms using the template provided below:

| Past Performance Template |  |
| --- | --- |
| Project Title: | Period of Implementation: |
| Funding Organization/Contact Person: | Total Budget Amount: |
| Project Description (please include the goals and objectives, as well as the methodology used): |  |
| Project Outcomes (qualitative and quantitative): |  |

- Cost Proposal

2.1. Budget

Offerors are instructed to complete boxes highlighted in gray. Pricing must be presented in AMD:

| Deliverable | Deliverable Description | Cost, AMD |
| --- | --- | --- |
| 1. | Inception report, including a detailed work plan for the Project, and the Methodologies for each of the Project Components. |  |
| 2. | Comprehensive methodology for functional and institutional review, including tools for self-assessment and modernization and a unified methodology for determining the organizational type |  |
| 3. | Training program and materials for personnel responsible for functional and structural analysis |  |
| 4. | Comprehensive report on functional and institutional analysis, including identified issues, and recommendations for improving the structure and functionality of public administration bodies. |  |
| 5. | Structural and functional reengineering recommendations, including the examples of the best international practice |  |
| 6. | Plan identifying opportunities for delegating projects to the private sector and developing management tools. |  |
| 7. | Complete inventory and mapping of current public administration system, including digital register creation |  |
| 8. | Development of a unified typology for classifying public administration bodies |  |
| 9. | Report on stakeholder consultations about the proposed recommendations and amended recommendations |  |
| 10. | Project implementation document package |  |

This proposed rate is exclusively for the Offeror’s level of effort and the rate must include all profit, fees, etc. Other assignment-related costs will be approved on a reimbursable basis in accordance with CNFA’s Consultant Expenses Policy, which may be shared with the Offeror upon request and will be incorporated into the final executed award with the successful Offeror.

- Tax Considerations

Offerors are made aware of CNFA’s tax status in Armenia. CNFA is tax-exempt in Armenia. Offers submitted must comply with these tax considerations.

- Bank Account

Offerors are instructed to complete boxes highlighted in gray:

| Does the Offeror have an active bank account? | ☐ Yes ☐ No |
| --- | --- |
| If yes, provide the Offeror name associated with the Bank Account if selected for eventual award. | Offerors must provide the name associated with their Bank Account, if applicable, here |

All deliverables must be submitted in both English and Armenian languages.