Women Empowerment for Wellbeing (WoW)

Establishment of the Network for Displaced Women with Disabilities

Call for proposals – to conduct (1) participatory analysis of existing social services for displaced women with disabilities, (2) an analysis of existing groups or networks of and for displaced women with disabilities, (3) to identify potential leading organization to run a network for and with women with disabilities, (4) to identify potential founding members of the network and (5) to organize the first network meeting.

Guideline for Applicants

- Context

WoW is a regional South Caucasus project, commissioned by the German Federal Ministry for Economic Cooperation and Development (BMZ) and implemented by Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ). The goal of the project is to strengthen the Rights, Representation, and Resources of conflict-affected women.

The project serves the following objectives:

- eliminate gender-based discrimination and provide victims of gender-based violence with protection and support services;

- increase employment and income opportunities for vulnerable displaced women, refugee women, women in refugee-like situation and local women;

- empower the target group, especially youth and women, and their organizations to promote change in their communities;

- support governmental and non-governmental institutions for a strategic embedding of the measures in gender and equality rights.

Key areas of intervention in Armenia are:

- Raise awareness on gender stereotypes and traditional role models;

- Improving protection and support services for vulnerable displaced women and victims of gender-based violence;

- Improving the psychosocial well-being of the target group;

- Increasing employment and income opportunities for women;

- Supporting governmental and non-governmental institutions in the implementation of measures in the field of gender equality.

- Objective of the Call

GIZ within Women Empowerment for Wellbeing (WoW) announces a call for proposals – to conduct (1) participatory analysis of existing social services for displaced women with disabilities, (2) an analysis of existing groups or networks of and for displaced women with disabilities, (3) to identify potential leading organization to run a network for and with women with disabilities, (4) to identify potential founding members of the network and (5) to organize the first network meeting.

People with disabilities face in Armenia many barriers to live an inclusive and independent life. In addition to limited access to social service locations or limited available information, the lack of social networks remains a major barrier. Displaced women from Nagorno-Karabakh, who have disabilities, are more likely to experience exclusion from societal and political life through their intersectional discrimination as displaced, as women and as persons with disabilities.

The aim of this call is to develop a network for and with displaced women with disabilities to ensure that:

- displaced women with disabilities are better integrated into society, their concerns reach the public and gain political attention;

- the efforts of different organisations working in the field of displaced women with disabilities are aligned, synergies created and pooling of resources established;

- the power of persuasion, advocacy and influencing the political agenda is ensured through the collaborative work of the actors within the network.

In order to achieve the above objectives and to ensure the sustainability of the network, the following services are expected to be provided in the first implementation phase

- Development of an analysis of existing groups, initiatives and networks with and for displaced women with disabilities;

- Carrying out an analysis to identify potential leading organization working on the issue of displaced women with disabilities (or in a related field) to run a network for and with women with disabilities;

- Conducting an analysis to identify existing organisations, networks and physical persons (representatives of the target group, experts etc.) for joining the network. As the final result, an initial list of possible network members should be created.

- Carrying out an analysis of existing social services for displaced women with disabilities. Subsequently, in cooperation with displaced women with disabilities and other relevant stakeholders, such as political representatives and civil society organisations, a pilot measure or revision of one or more existing social services that meet the needs of the target group should be developed in a participatory manner. Finally, a report/study should be submitted as the final product of the analysis carried out.

Please note that the implementation of the first phase should be completed by the 30th of November 2024, otherwise the task may be considered as not fulfilled.

During the second implementation phase

- A first meeting of the network should be organised in close cooperation with the leading organisation and the Ministry of Labor and Social Affairs. It should also include representatives of the identified organisations, experts and displaced women with disabilities. The meeting should determine the geographical location of the network (either nationwide or localised at regional level), establish a membership base and identify ways to secure sufficient funding. In addition, a concept paper, a network strategy, network guidelines and an operational plan should be developed with the members of the network.

The implementation of the second phase should take place in the first quarter of 2025.

Brief description of the requirements for the leading organisation of the network:

The leading organisation should play the main role not only in setting up the network but also in providing technical and organisational support, either for an indefinite period or until the network and its members have the capacity to run the network independently. Close cooperation with the Ministry of Labor and Social Affairs is expected to ensure the sustainability of the network.

The main tasks of the organisation will be to pro-actively communicate with and coordinate future initial members and key actors of the network and plan with them further activities. The analysis of social services as well as the development of new or revision of existing services should will serve as part of the operational plan and thus as a basis for further work of the network (its advocacy of service(s) at the political level for future implementation, exchange of information and experiences, or as a starting point for further revision and implementation by civil society organisations).

Note: To carry out the listed analyses during the first implementation phase, organizations are expected to have at least one expert per assignment who can demonstrate his or her ability to conduct the described activities.

Note: Implementation of the first phase shall commence on 28 October and be completed by 30 November 2024.

Note: Each applicant can submit only one project proposal.

- Evaluation Process and Criteria

Only the participating companies registered in Armenia will be eligible for receiving the grant.

All projects submitted by applicants will be assessed according to the following steps and criteria

Administrative check and eligibility check

The administrative check will focus on the following criteria for the assessment:

- The deadline has been respected.

- The requested information is correct and complete.

- Minimum eligibility requirements are met. The eligibility verification will be done based on the supporting documents (registration certificate, legal statutes/Charter) requested by GIZ along with the application form. Any missing supporting document may lead to the rejection of the application on that sole basis.

Evaluation of applications

The evaluation of applications will focus on the capacities of applicants as well as on the quality of their project proposals crosschecked with submitted supporting documents. All eligible project proposals will be evaluated, and an average score will be calculated as the basis for ranking the project.

Scoring: The evaluation grid is divided into sections and subsections. Each subsection will be given a score between 1 and 5 as follows: 1 = very poor; 2 = poor; 3 = adequate; 4 = good; 5 = very good and between 1-20 again where 1 means very poor and 20 very good.

| Section | Maximum Score |
| --- | --- |
| 1. Financial and operational capacity | 30 |
| 1.1 Do the applicants have sufficient experience in project management? | 10 |
| 1.2 Do the applicants have sufficient experience in conducting analyses? | 8 |
| 1.3 Do the applicants have sufficient technical expertise? (Especially knowledge of the issues to be addressed) | 7 |
| 1.4 Do the applicants have sufficient management capacity? (Including staff, equipment and ability to handle the budget)? | 5 |
| 2. Relevance, effectiveness and feasibility of the action | 35 |
| 2.1 How relevant is the proposal to the objectives and priorities of the Call for Proposals? | 15 |
| 2.2 How innovative are the approaches in the proposal? | 5 |
| 2.2 Are the activities proposed appropriate, practical, and consistent with the objectives and expected results? | 10 |
| 2.3 Does the proposal contain objectively verifiable indicators for the outcome of the action? | 5 |
| 3. Sustainability of the action | 25 |
| 3.1 Will political actors be involved in the development or revision of existing social services? | 10 |
| 3.2 Is the analysis of the capacities of the selected management organization presented in a comprehensible manner? | 5 |
| 3.3 Engagement of the target group in planned activities. | 5 |
| 3.4 Will the way in which the activities are carried out have a positive and empowering effect on the target group? | 5 |
| 4. Budget and cost-effectiveness of the action | 10 |
| 4.1 Is the ratio between the estimated costs and the expected results satisfactory? | 10 |
| Maximum total score | 100 |

- Submission requirements

Interested applicants are expected to examine the Guidelines for Applicants in detail before preparing and submitting their applications. Applications that are submitted late, incomplete, or are non-responsive may result in the rejection of the proposal.

Applications can be submitted in English to the email address: anna.hovhannisyan@giz.de and maryna.natkhir@giz.de

Hand-written Proposals will not be accepted.

When submitting their proposals, applicants must follow all instructions, forms and specifications. Failure to submit an application package containing all the required information and documentation within the deadline specified may lead to the rejection of the proposal.

It is required to send the below-mentioned application package by email. The original documents will be required upon necessity.

| Application package | Information |
| --- | --- |
| Grant Application Form (Annex 1) | attached to the announcement as a separate annex |
| Budget & Budget Narrative Form (Annex 2) | attached to the announcement as a separate annex |
| Activity Plan (Annex 3) | attached to the announcement as a separate annex |
| Logical Framework (Annex 4) | attached to the announcement as a separate annex |
| CVs of the project team members demonstrating competency and any experience relevant to the execution of the proposed project | No special format is required |
| Organization’s registration certificate | Scan of the original registration certificate |
| Organization’s Statute (charter) | Scan of the original Statute (Charter) |
| Organisation’s portfolio/List of implemented projects (Annex 5) | attached to the announcement as a separate annex |
| Partnership Declarations (in case of consortium) | No special format is required |

It is strongly recommended to apply before the deadline to avoid any technical difficulties with submitting of the files.

Questions may be sent by e-mail until 11 October 2024 to the address listed below, indicating clearly the name of the call for proposals.

E-mail address: maryna.natkhir@giz.de

The applicants are urged to submit in their application package, particularly in CVs, only information relevant to the call and to avoid including personal information. The data submitted will be treated confidentially according to GIZ’s data protection rules and will not be disclosed to third parties.

With the submission of the application, the persons proposed in the implementation team express their consent regarding the review and evaluation of personal data by the GIZ. The data is provided for confirmation and clarification of information regarding the submission of the applications to the Call for proposals within EPIC.

- Timeline

| 3 October 2024 | Opening date for call for proposal |
| --- | --- |
| 7-11 October 2024 | Q&A period |
| 17 October 2024 | Closing date for call for proposal |
| 23 October 2024 | Selection of winners |
| 28 October 2024 | Contract tentative start date (planned) |
| 30 November 2024 | Contract tentative end date (planned) |

- Project implementation, reporting and monitoring

Immediately after the financing starts, applicants shall start implementing their projects based on the timeline and milestones included in the contract. Applicants shall present to the project implementation report, justifying the performed expenses with respective invoices and statements.

EPIC shall manage on-the-spot monitoring for each grant contract. In this regard, the programme has the right to carry out on-the-spot checks and inspections on the premises of grant beneficiaries. The data collection will be shared with the applicants and monitoring specialist will conduct introductory sessions in this regard.

- Application package

Annex 1. Grant Application Form

Please download the Grant Application Form as attached to the announcement, fill it in and include it in your application package.

Annex 2. Budget & Budget Narrative Form

Please download the Budget Form as attached to the announcement, fill in both sheets (budget and budget narrative) and include it in your application package.

Annex 3. Activity Plan

Please download the Work Plan Form as attached to the announcement, fill it in and include it in your application package.

Annex 4. Logical Framework

Please download the Logical Framework Form as attached to the announcement, fill it in and include it in your application package.

Annex 5.  Applicant’s experience Form

Please download the applicant’s experience Form as attached to the announcement, fill it in and include it in your application package.

Supporting Documents

- CVs of proposed staff

- Registration certificate of your organization

- Legal Statute (Charter) of your organization

- Partnership declaration/agreement, in case of consortium

Please note that the organization carrying out the analyses can also be considered in the list of possible leading organizations of the network.